**For More Health**

**Milestone**

**App Milestone:**

MS01 - 08 /03/2018 - 08/03/2018 (Auth Package Design: 1 Working Days)

* + - * Login Screen
      * Sign Up Screen
      * Forgot Password
      * Change Password
      * Child Registration
      * PIN

MS02-09/03/2018 -13/03/2018 ( Food Package Design: 3 working days )

* + - * Food Buy
      * Fridge
      * Non Fridge
      * Feeding

MS03 - 14/03/2018 - 15/03/2018 (Auth Package Functionality: 2 Working Days)

* + - * Login Screen
      * Sign Up Screen
      * Forgot Password
      * Change Password
      * Child Registration
      * PIN

MS04-16/03/2018 -23/03/2018 ( Food Package Functionality: 6 working days )

* + - * Food Buy
      * Fridge
      * Non Fridge
      * Feeding

MS05-26/03/2018-28/03/2018 ( Dress Package: 3 working days )

* + - * Dress Store
      * Dress show
      * Dressing up

MS06-29/03/2018-30/03/2018 (Mission Package: 2 working days)

* + - * Mission Type Selection
      * Mission Selection
      * Mission Camp

MS07-02/04/2018-03/04/2018 (Sleep Package: 1 working day)

* + - * Sleep Screen
      * Quiz screen
      * Wake up Screen
      * Random Quiz

MS08-04/04/2018-04/04/2018 (Reference Package: 1 working day)

* + - * Setting Screen